## Issue List
Issue | Sales / Service | Object | Assigned To | Status | Date Opened | Date Fixed | Confirmed Fixed | Comments
Issue with applying Queue Name on SR. Does not save queue. When adding a queue, it does not save it | Service | Service Request | Sono | Resolved |  |  | 2025-07-21
Trigger script for allowing who can be assigned to a queue is not working | Service | Service Request | Sono | Resolved |  |  | 2025-07-21 | Should get an error if assigning to someone who is not in the queue
UI does not show required fields to the user (Category, Problem Description) | Service | Service Request | Sono | Resolved |  |  | 2025-07-21 | We get an error after submitting that a required field is not filled in
Add Account Number and Customer Type to Account DCL | Service | Service Request | Sono | Resolved |  |  |  | 7/21: This is showing now, but the list only shows 10 items so cannot see the one I need to select. We normally select the Customer Type = Bill To. I can enter "ACI01 Bill To" and it does bring up the account.
Remove Work Order | Service | Service Request | Sono |  | 2025-08-21 |  |  | Need to remove from the Create menu as well. I thought this was done, but I see Work Orders panel when I open a SR
Quick Close trigger script - not assigning the CategoryId | Service | Service Request | Sono | Resolved |  |  | 2025-07-21
Add the additional page during create for Vehicle/Part Information and Customer Service pages | Service | Service Request | Sono | Working as expected. Need to discuss |  |  |  | Normally we can click on "Save and Continue" to get to these fields or "Save and Close". Now, there is just a "Create" button and then we have to go back into the SR to add fields
Where does it show the milestones / time remaining / due date on SR? | Service | Service Request | Sono |  |  |  |  | Need to modify the Spotlight section
Remove Work Order from the Create button | Service | Service Request | Ajay
Remove icons under Redwood Sales tab: Deal Registrations / MDF Budgets / MDF Requests / MDF Claims / Campaigns / Enrollments / Products | Sales | Home Screen | Ajay |  | 2025-08-21 | 2025-08-22 |  | These to be hid from Structure EL Expression
I assume that Partners and Partner Contacts are part of the old Partner Management Tab? I am getting an error when opening these "You cannot access this information because the object isn't enabled in Adaptive Search" | Sales | Home Screen | Sono |  | 2025-08-21 |  |  | Please enable them in Configure Adaptive search, objects and field and do a publish
Dashboards are missing under the Redwood Sales tab | Sales | Home Screen | Sono |  | 2025-08-21 |  |  | Try adding Sales Manager role
I do not see Business Plans in the Redwood Sales tab | Sales | Home Screen | Sono |  | 2025-08-21
Under My Accounts the record set is defaulted to "I am on the team or territory". We do not use teams or territories. Can we default this to "I own" | Sales | Accounts | Ajay |  | 2025-08-21 | 2025-08-25 |  | These changes can be done in Manage Saved Search, inactive in all unused searches
For Account Details, all of the fields under the "Other Information" section are supposed to be read only. This information comes from Oracle EBS | Sales | Accounts | Ajay |  | 2025-08-21 | 2025-08-25 |  | These can be done in VB, there is a checkbox for Readonly option, if it is supposed to be conditionally required we can add field level conditions
When I am on the "My Accounts" page for a particular account, and I want to add an Opportunity, how do I do this? We have taught our sales team to always find the account first in Workspace, then add an opportunity, activity, contact, etc. | Sales | Accounts | Oracle |  | 2025-08-21 |  |  | There should be a way to add opportunities, activities, contacts, etc. when on a particular account. Is the filter box the only way? Yes, we can add from Create Smart actions
On the My Accounts page for an account, remove the Team panel. Move Leads and Quotes to the end | Sales | Accounts | Ajay |  | 2025-08-21 | 2025-08-25 |  | Can be updated from Panel Container
I do not see any panel for Activities on the My Accounts page. Can we add this? | Sales | Accounts | Ajay |  | 2025-08-21 | 2025-08-25 |  | Can be updated from Panel Container Have to do Activity Configuration
On the view for list of accounts, can we add default fields for all (we had this before): Party Site Name, Account Number, Customer Type, Major Customer Group, Owner, Rollup Group. Remove Primary Industry | Sales | Accounts | Ajay |  | 2025-08-21 | 2025-08-25 |  | This can be updated from Saved Searches
Can we rename Assets to Orders? We had this renamed before | Sales | Accounts | Ajay | lavanya has to update | 2025-08-21
Where can we find the Notes section for accounts? | Sales | Accounts | Sono |  | 2025-08-21 |  |  | We use Notes on accounts now
Remove Deal Registrations from the bottom of the page for My Accounts | Sales | Accounts | Ajay |  | 2025-08-21 | 2025-08-25 |  | Remove from Structure
When on screens to search and find an account, can we add the Account Number and Customer Type to the DCL | Sales | All | Oracle |  | 2025-08-21 |  |  | This was done for SR's Document to be shared
When adding a new Opportunity, the Account field is not required | Sales | Opportunity | Ajay |  | 2025-08-21 |  |  | VB Change
We had two fields that were only shown depending on the value of the Opportunity Type field. Now, they are showing on the main Create Opportunity page | Sales | Opportunity | Ajay |  | 2025-08-21 |  |  | Other 1X Types field should only show if the Opportunity Type = "Other 1X". IOP Type field should only show if the Opportunity Type = "IOP". See Create Opportunity screen print | VB Change
When adding a new Opportunity, we need to add a product from the catalog and FY Amount. These fields do not show up on the Create Opportunity page now. So we get an error from our trigger script about needing to add one product type. Due to this, we cannot create an opportunity | Sales | Opportunity | Oracle |  | 2025-08-21 |  |  | See Create Opportunity screen print. Can we add this to the Create Opportunity page? We don't want to have to go back and have to add a product. This is mandatory every time we add an opportunity
On the My Open Opportunities page, remove the Teams, Competitors | Sales | Opportunity | Ajay |  | 2025-08-21
Remove the Estimated Price from Revenu | Sales | Opportunity | Ajay |  | 2025-08-21
Where is the sales coach in Redwood? | Sales | Opportunity | Oracle |  | 2025-08-21 |  |  | Sales Orchestration to be setup
Question: How long will we be able to have the Redwood and Non-Redwood pages when we go to production? | Sales/Service | All | Oracle |  | 2025-08-21
On pages converted to redwood, the fields all are shown left to right, where before they were by column. So the order is completely different now. | Sales | All | ? |  | 2025-08-21 |  |  | See screen print of Create Opportunity
Question: What is the Hierarchy option for Accounts? | Sales | Accounts | Oracle |  | 2025-08-21 |  |  | Not sure if we need this or not? If not, we can remove
When adding a new Appointment, we need to add a "Meeting Type". These fields do not show up on the Create Activity page now. So, we get an error from our trigger script about needing to add one meeting type. Due to this, we cannot create a new activity, I do not see these fields | Sales | Activities | Oracle |  | 2025-08-21 |  |  | See screen print of Create Appointment. Meeting Type checkboxes appeared on the first page.
When creating a contact, there is no field for associating to an account. There is a box for "Use Account Address" which is greyed out since there is no account selected. We used to be able to select an account for a contact. Even when I go to details, there is no way to associate to an account | Sales | Contacts | Oracle |  | 2025-08-21
What is the Competitors panel on My Open Opportunities for an account? We have a custom field for competitors but it is not populating this | Sales | Opportunity | Oracle |  | 2025-08-21 |  |  | Perhaps we need to remove the custom field and use this new Competitor OOTB field?
Do we need to show Partners on the Open Opportunities page for an account? | Sales | Opportunity | Crystal |  | 2025-08-21 |  |  | Need to ask the business about this. I don't think we will need
What is Revenue Lines? | Sales | Opportunity | Oracle |  | 2025-08-21 |  |  | Defaults to record sets "Sales Credit Allocation" and "I am a credit receiver". May need to remove
Where can we find the Notes section for opportunities? | Sales | Opportunity | Oracle |  | 2025-08-21
Are we OK to use Quotes as part of our contract? | Sales | Quotes | Oracle |  | 2025-08-21 |  |  | We have not used this before and does not show up on any screen now. Our collision team is interested in using quotes
Quotes and Quote lines shows an error about needing to enable in adaptive search to use | Sales | Quotes | ? |  | 2025-08-21
What are forecasts? | Sales | Opportunity | Crystal |  | 2025-08-21 |  |  | Need to ask the business about this. I don't think we will need
What is Sales Performance? | Sales |  | Oracle |  | 2025-08-21 |  |  | Nothing shows up here. Looks like can create a contest or goal or KPI. May need to remove
Show additional fields on My Open Opportunities: Opportunity Type, FY Amount, Target Decision Date, Schedule, Owner, Last Updated Date | Sales | Opportunity | Ajay |  | 2025-08-21 |  |  | We show these fields today for everyone by default
What are Express Reports? Is this easy enough for Sales to create their own reports (and only see their own data) | Sales | Home Screen | Oracle |  | 2025-08-21 |  |  | yes, this is an easy way to create reports for all users, we can go through this in our next call
Under Opportunities there is a "Send Email" option and it uses Generative AI. Need to figure out if we want to use this. It requires an email template | Sales | Opportunity | Crystal |  | 2025-08-21
Need to determine any changes needed to make the O365 integration to work. Getting error in TEST and is depreciated in production | Sales | O365 | Sono |  | 2025-08-21
At the top of all pages is a box with a checkbox and Service Request is greyed out. Not sure what this is and should it work? | Sales | All | Sono |  | 2025-08-21

## Screen Prints
Create Opportunity
Create Appointment | Meeting Types:

## Testing
Item Tested | Sales / Service | Validated - Successful | Owner | Comments
Product type is required based on the Quick Close selected | Service | 2025-07-21 | Crystal
Quick Close - validate all fields populating: | Service | 2025-07-21 | Crystal
CategoryId |  |  |  | Needed to be switched to Category Name (instead of using Id)
StatusCd
ResolveOutcomeCd
ResolutionCd
AssigneeResourceId
ResolveDescription |  |  | Crystal
Invoke Visual Session button | Service | 2025-07-21 | Crystal
Milestones | Service |  | Crystal
Auto-reply email | Service |  | Crystal
Messages: | Service |  | Crystal
Smart Text
Response to Customer
Internal Info Requst
Internal Note
Review Update Status - verify status changes when responding to message | Service |  | Crystal
Required fields: | Service |  | Crystal
Category
Problem Description
Upload attachment and add to message | Service |  | Crystal
Validate all fields are populating on all pages | Service |  | Crystal
Add a relationship between 2 SR's | Service |  | Crystal | New functionality?
Email for Product Management SR's | Service

## Trigger Scripts
Service:
Service Request Trigger Scripts:
Message:
Sales (will need to convert manually if needed)
Account Trigger Scripts:
Opportunity Trigger Scripts:
Activity Validation Rules:
Relationship Trigger Scripts: